## Sheet1
|  | Planned Activities | Completed Activities
| 2019-06-20 | Ideation | ✓
| 2019-06-21 | Writing down concepts | ✓
| 2019-06-22 | Setting up Git, identifying features | ✓
| 2019-06-23 | Detailed planning, defining scope | ✓
Sprint 1 target features: | 2019-06-24 | Sprint 1 | Drag and Drop for cards, hand layout
Drag and drop cards. | 2019-06-25 | Sprint 1
Modifiable card text | 2019-06-26 | Sprint 1
Playing cards through drop | 2019-06-27 | Sprint 1
Draw/Discard decks | 2019-06-28 | Sprint 1
2019-06-29
| 2019-06-30 | Evaluation of Sprint 1
Sprint 2 target features: | 2019-07-01 | Sprint 2
Characters that add cards | 2019-07-02 | Sprint 2
Equipment that adds cards | 2019-07-03 | Sprint 2
Characters equip equipment | 2019-07-04 | Sprint 2
| 2019-07-05 | Sprint 2
2019-07-06
| 2019-07-07 | Evaluation of Sprint 2
Sprint 3 target features: | 2019-07-08 | Sprint 3
Enemies | 2019-07-09 | Sprint 3
Somewhat functional encounters | 2019-07-10 | Sprint 3
| 2019-07-11 | Sprint 3
| 2019-07-12 | Sprint 3
2019-07-13
| 2019-07-14 | Evaluation of Sprint 3